## Jaarplanning en verdeling
| Responsible | Policy plan | September | Oktober | November | December | Januari | Februari | Maart | April | Mei | Juni | Juli | Augustus
Events | Lois |  | Brainstorm | Present at study association borrels | CoBo | Spirit day | Waffles NYS | Valentines |  | Recruitment event |  | Clitbo
College talks | Melanie? |  | Januari: Mailing teachers; Februari: Mailing teachers | Werving
Cobo and policy plan presentation | Maas |  | September: PV piece; Oktober: Planning; November: Cobo
Faculty introductions | [9 empty] | Brainstorm | organize talks | (get promo stuff?) |  | Keep the talks
New years survey | Nina |  |  | What do we want | PV piece input council beginning of november | Input from the council must be received by the end of November and the first version must be completed in early December | Enquete online | Processing surveys, handing out prizes | Archiving
Promomaterial | Joanna |  | Brainstorm/buy | Brainstorm/buy | Brainstorm/buy | Brainstorm/buy | Brainstorm/buy | Brainstorm/buy | Brainstorm/buy | Brainstorm/buy | Brainstorm/buy | Brainstorm/buy
Council clothing | Chris, Maas |  | September: Bespreken op PV; Oktober: Bestellen voor iedereen
Social media | Zazi, Lois, Joanna |  | Posten | Posten | Posten | Posten | Posten | Posten | Posten | Posten | Posten | Posten
To Dah Loo | Joanna, Nina |  | appointment and topics | appointment and topics | appointment and topics | appointment and topics | appointment and topics | appointment and topics | appointment and topics | appointment and topics | appointment and topics
Website | Maas |  | Update | Update | Checking |  | Updaten | Updaten | Updaten | Updaten | Updaten | Updaten | Updaten
Recruitement | Nina, Maas |  | make planning | make planning |  |  | Do planning | Do planning | do planning | evaluate
BVO | Maas
Dossiers Faciliteiten | Responsible |  | September | Oktober | November | December | Januari | Februari | Maart | April | Mei | Juni | Juli | Augustus
Catering | Eloïse, Zazi
Diversity | Zazi, Maas, Nina |  | September: Sounding board; Februari: Event?
Spirit Day (Purple Friday) | Eloïse |  | November: planning; December: doing it
Facility talks | Joanna, Maas |  | Get in contact | Have meeting | Get input | Have meeting | get input | have meeting | get input | have meeting | get input | have meeting
Talks with gijs | Joanna, Maas |  | get in contact with Gijs | Talk | Talk | Talk | Talk | talk | Talk | Talk | Talk | Talk
Mental health | Zazi, Lois |  | September: What does the CSR do
Social safety | Nina, Lois |  | Quarterly meeting | Poster campagne | Poster campagne | Quarterly meeting
Pronouns | Zazi
Accesibility |  |  | Kijken wat er geregeld wordt, contact leggen met DWG | DWG monitoren | Handleiding fixen evt | Handleiding fixen evt | Uitwerken eindversie en bespreken argumenten | Bespreken bij IO | Verwerken IO, bespreken BO | Implementatie monitoren | Implementatie monitoren | Implementatie monitoren
Sustainability
Fileholder | Number of files
Maas | 8
Joanna | 4
Nina | 5
Zazi | 5
Lois | 4