# Summary of main points:

Planning of the elections

- Planning requires setting up a draaiboek.

- More collaboration between the FSRs and the CSR early on to make it more effective.

- Plan the entire process for Kieswijzer earlier. Setup the software of the Kieswijzer already before the kandidaatstelling.

- Order and plan merchandise from January onward and keep them connected to a theme related to the UvA students (like the privacy theme).

- PR committee needs more help (setting a Taskforce Elections) and work more earlier from January on the Elections taskforce.

- Lack of call to vote from CSB

- Prevent overlapping with major other events during elections week (ex. Health week this year) and prevent overlap with exams period. Work with CSB about this.

- Shorter the period of announcing the outcome of the elections

- Put pictures of the candidates in the voting website.

- Verify all the parties emails to avoid miscommunication.

- During announcing period, find translator for international students.

Contact with BC

- Extra contact person besides Bart to avoid miscommunication and delays in replying.

- Take CSR input in decision making into account and not leave practical with CSR.

- Communication should be neutral but also informing (this also done in Folia magazine, website, video).

- Protocol about communication for BC-CSB

- Role of BC should not overshadow CSR decisions for example with the neutrality of the elections and the equal treatment of campuses.

- BC should make awareness campaign during introductory period/Intreeweek

- Focus on promoting on Screens to reach out to students.

- Send email to vote one week prior to the elections.

- Themes of the computes and Lecture slides should be about elections.

Kieswijzer

- Change of link to Kieswijzer was not communicated clearly and was last minute. Should work on the kieswijzer early on and avoid delays and review carefully before launching it.

- Pay attention to the URL on the banners.

- Email the parties earlier so everyone can attend.

Promotion / awareness about elections

- Inform parties about promoting full week and pointing out that this will help overall with the turnout for the elections.

- Send student mail (CSB) to the students and BC should work more on sending emails even during the elections week.

- Creative promotions should be promoted earlier and avoid time pressure

- There should more information that reflects the easiness of starting your own party.

- Email the Lecturer to include a slide and give some time, 2mins, for students to vote during lectures.

Campaign

- Campaign training? Council disagrees whether to offer this or whether this should be offered by parties if needed

- Code of conduct for campaign period should be prepared as early as possible and forwarded to the parties to avoid any unfairness and misconduct.

- CSR being more present on media during the year and pre-announcement of elections, introduction sessions to elections

- Announce candidacy information earlier and help the parties promote find candidates early on from February.

- Promote during Kickoff day organized by UvA.

- Hire more students to help with putting the elections posters.

- The posters should be delivered at one month before elections.

Kieswijzer

- 3/5 answers

- Make parties clear what expected, inform earlier

- Extra costs

- Not let BC have too strong say and delay the project

- English use needs evaluation / revision

- Set up kieswijzer early in year, let parties fill statements and their position after candidacy

- Budget leftover to invest in Kieswijzer for next year.

Folia

- Distribute all campuses

- Overall positive

Booking facilities

- Book early as possible to avoid any reserved places during the elections and improve the communication between the FSRs and the Facility services.

- Make sure everyone receives code of conduct or  regulations about the elections.

Merchandise and Posters

- Pay attention to the posters and do it earlier not last moment and send it via email for the council members to give feedback and have time to change.

- Fliers about elections information and candidacy should be done early on from January and spread all over UvA faculties.

- Posters should be in Dutch and English and check with FSRs which one they will need.

- There should be a special area in the campuses only for putting election posters.

CSB

- Send out a call to all students to vote